## IT SOW
CNA421_Final_Persian STATEMENT OF WORK
ORGANIZATION
PROJECT NAME | Get lambda instance talking to web server and RDS
CLIENT | David Roy
SOW VERSION NUMBER | CNA421.Final.Persian
CLIENT POINT OF CONTACT | 4252352352
DATE PREPARED: 05.30.2021 |  | AUTHOR: Saeid Nahali
PROJECT MANAGER | Saeid Nahali , Mohammad Pakizeh jam
BEGIN DATE | END DATE | PROJECT DURATION
06.03.2021 | 06.15.2021 | 15 days
PROJECT TEAM
NAME / TITLE | CONTACT INFORMATION
Saeid Nahali | saeidnahali@outlook.com
Mohammad Pakizeh jam | mohammad.pakizehjam@gmail.com
PROJECT
INTRODUCTION ¦ description without requirement details
Get web server on EC2 up and responding to web browser requests.Get RDS instance launched and data populated.Get lambda instance talking to web server and RDS
BACKGROUND ¦ what led to the necessity of this project?
All the services will be connect to AWS EC2
RESOURCE REQUIREMENTS
https://aws.amazon.com/
FEE SUMMARY
Steps | Time | TOTAL:
Amazon simple storage service(S3) | Per/Year | 353.28
Amazon RDS for sql server | Per/Year | 1456.68
Amazon EC2 | Per/Year | 61.06
Elastic Load balancing | Per/Year | 36.87
Technical Support | Per/Year | 6000
Total Estimate cost per year(Before Tax)
28894.68
MILESTONES
EST DELIVERY DATE | PROJECT MILESTONE TITLE
06.03.2021 | Statement of Work
06.06.2021 | Get web server on EC2 up and responding to web browser requests.
06.09.2021 | Create RDS instance and Connect from EC2
06.12.2021 | Get lambda instance talking to web server and RDS
06.15.2021 | Ready to present
DELIVERABLE MATERIALS
what is the final product to be supplied to the client?
lambda instance talking to web server and RDS
AUTHORIZATION
CLIENT | SIGNATURE
| PRINTED NAME | David Roy
| DATE | 06.02.2021
PROVIDER | SIGNATURE
| PRINTED NAME | Saeid Nahali Mohammad pakize jam
| DATE | 06.02.2021